## Gantt Chart
AklatBayon v2 — Project Gantt Chart
FEATI University Library Management System — Feb 26 to Mar 25, 2026
[6 empty] | FEBRUARY 2026 |  |  | MARCH 2026
| Task Name | Status | Start | End | Days | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Phase 1: Project Setup & Foundation
| Project initialization & repo setup | Complete | 2026-02-26 | 2026-02-26 | 1d
| Netlify deployment config | Complete | 2026-02-26 | 2026-02-26 | 1d
| CSS styling & responsive design | Complete | 2026-02-26 | 2026-02-27 | 2d
| Landing page (index.html) | Complete | 2026-02-26 | 2026-02-26 | 1d
| Login page with RFID support | Complete | 2026-02-26 | 2026-02-26 | 1d
| Package.json & dependencies | Complete | 2026-03-11 | 2026-03-11 | 1d
Phase 2: Core UI Shell & Authentication
| Authentication system (auth.js) | Complete | 2026-02-26 | 2026-02-26 | 1d
| LocalStorage data store (store.js) | Complete | 2026-02-26 | 2026-02-26 | 1d
| Permission-based sidebar | Complete | 2026-02-26 | 2026-02-26 | 1d
| App shell & header (app.js) | Complete | 2026-02-26 | 2026-02-26 | 1d
| Dashboard with stats & charts | Complete | 2026-02-26 | 2026-02-27 | 2d
| Dark mode toggle | Complete | 2026-02-26 | 2026-02-26 | 1d
| Profanity filter (EN + Tagalog) | Complete | 2026-02-26 | 2026-02-26 | 1d
Phase 3: User & Role Management
| User CRUD (users.html) | Complete | 2026-02-26 | 2026-02-27 | 2d
| Role management (7 roles) | Complete | 2026-02-26 | 2026-02-27 | 2d
| Permission assignment (23 perms) | Complete | 2026-02-26 | 2026-02-27 | 2d
| Student records CRUD | Complete | 2026-02-26 | 2026-02-27 | 2d
Phase 4: Catalog Management
| Books CRUD with ISBN / call number | Complete | 2026-02-26 | 2026-02-27 | 2d
| Authors management | Complete | 2026-02-26 | 2026-02-27 | 2d
| Publishers management | Complete | 2026-02-26 | 2026-02-27 | 2d
| Categories (hierarchical) | Complete | 2026-02-26 | 2026-02-27 | 2d
| LCC Classification browser | Complete | 2026-02-26 | 2026-02-27 | 2d
| LOC Book Search integration | Complete | 2026-02-26 | 2026-02-27 | 2d
| Barcode generation (JsBarcode) | Complete | 2026-03-09 | 2026-03-09 | 1d
| Advanced OPAC with filters | Complete | 2026-03-09 | 2026-03-09 | 1d
Phase 5: Circulation & Reservations
| Book issue & return | Complete | 2026-02-26 | 2026-02-27 | 2d
| Book renewal (role-based limits) | Complete | 2026-03-09 | 2026-03-09 | 1d
| Reservation system (queue & expiry) | Complete | 2026-03-09 | 2026-03-09 | 1d
| Overdue auto-fine processing | Complete | 2026-03-09 | 2026-03-09 | 1d
| Fine block threshold enforcement | Complete | 2026-03-09 | 2026-03-09 | 1d
| Borrower profile with QR code | Complete | 2026-03-09 | 2026-03-09 | 1d
Phase 6: Finance & Administration
| Fine management (admin) | Complete | 2026-02-26 | 2026-02-27 | 2d
| My Fines page (student/faculty) | Complete | 2026-03-09 | 2026-03-09 | 1d
| Inventory view | Complete | 2026-02-26 | 2026-02-27 | 2d
| Reports & analytics | Complete | 2026-02-26 | 2026-02-27 | 2d
| RFID attendance tracking | Complete | 2026-02-26 | 2026-02-27 | 2d
| Audit log system | Complete | 2026-02-26 | 2026-02-27 | 2d
| System settings (30+ params) | Complete | 2026-02-26 | 2026-03-09 | 12d
Phase 7: Backend Migration (Neon PostgreSQL)
| Netlify Neon DB provisioning | Complete | 2026-03-11 | 2026-03-11 | 1d
| Drizzle ORM schema (16 tables) | Complete | 2026-03-11 | 2026-03-11 | 1d
| Database migration to Postgres | Complete | 2026-03-11 | 2026-03-11 | 1d
| REST API serverless function | Complete | 2026-03-11 | 2026-03-11 | 1d
| Database seed function | Complete | 2026-03-11 | 2026-03-11 | 1d
| Frontend API client (api.js) | Complete | 2026-03-11 | 2026-03-11 | 1d
| Hybrid Store (API + localStorage) | Complete | 2026-03-11 | 2026-03-11 | 1d
| Deploy & seed production DB | In Progress | 2026-03-11 | 2026-03-12 | 2d
Phase 8: Security Hardening
| Password hashing (bcrypt/argon2) | Not Started | 2026-03-13 | 2026-03-14 | 2d
| JWT session tokens | Not Started | 2026-03-13 | 2026-03-15 | 3d
| Server-side auth middleware | Not Started | 2026-03-14 | 2026-03-16 | 3d
| Rate limiting & brute force prot. | Not Started | 2026-03-15 | 2026-03-16 | 2d
| Input sanitization (server-side) | Not Started | 2026-03-16 | 2026-03-17 | 2d
| RBAC enforcement on API | Not Started | 2026-03-16 | 2026-03-18 | 3d
Phase 9: Testing & QA
| API endpoint testing | Not Started | 2026-03-18 | 2026-03-19 | 2d
| Cross-browser compatibility | Not Started | 2026-03-19 | 2026-03-20 | 2d
| Data integrity validation | Not Started | 2026-03-19 | 2026-03-20 | 2d
| User acceptance testing (UAT) | Not Started | 2026-03-20 | 2026-03-22 | 3d
Phase 10: Production Launch
| Final deploy & smoke test | Not Started | 2026-03-23 | 2026-03-23 | 1d
| Documentation & handover | Not Started | 2026-03-23 | 2026-03-24 | 2d
| GO LIVE | Milestone | 2026-03-25 | 2026-03-25 | 1d
Legend: ■ Complete ■ In Progress ■ Not Started ◆ Milestone ░ Weekend ▌ Today
AklatBayon v2 — FEATI University — IT415 Assignment #4 — Generated March 11, 2026