## Gantt Chart
AklatBayon v2 — Full Project Gantt Chart
FEATI University Library Management System — Feb 2026 to Mar 2027 (Prototype to Production)
[5 empty] | 2026 | [10 empty] | 2027
| Task Name | Status | Start | End | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Phase 1: Project Setup & Foundation
| Project init, repo setup, Netlify config | Complete | Feb 2026 | Feb 2026
| CSS styling & responsive design | Complete | Feb 2026 | Feb 2026
| Landing page, login, welcome pages | Complete | Feb 2026 | Feb 2026
| Package.json & dependency management | Complete | Mar 2026 | Mar 2026
Phase 2: Core UI & Authentication (Prototype)
| Auth system, session management | Complete | Feb 2026 | Feb 2026
| localStorage data store (store.js) | Complete | Feb 2026 | Feb 2026
| Permission-based sidebar & app shell | Complete | Feb 2026 | Feb 2026
| Dashboard with stats & charts | Complete | Feb 2026 | Mar 2026
| Dark mode, profanity filter | Complete | Feb 2026 | Feb 2026
Phase 3: User, Role & Student Management
| User CRUD & role management (7 roles) | Complete | Feb 2026 | Feb 2026
| 23 permissions across 8 groups | Complete | Feb 2026 | Feb 2026
| Student records CRUD | Complete | Feb 2026 | Feb 2026
Phase 4: Catalog Management
| Books, Authors, Publishers, Categories CRUD | Complete | Feb 2026 | Feb 2026
| LCC browser & LOC API integration | Complete | Feb 2026 | Feb 2026
| Barcode generation & advanced OPAC | Complete | Mar 2026 | Mar 2026
Phase 5: Circulation, Reservations & Fines
| Book issue, return & renewal | Complete | Feb 2026 | Mar 2026
| Reservation system (FIFO queue, expiry) | Complete | Mar 2026 | Mar 2026
| Auto fine computation & block threshold | Complete | Mar 2026 | Mar 2026
| Borrower profile with QR code | Complete | Mar 2026 | Mar 2026
Phase 6: Administration & Reporting
| Fine management & My Fines page | Complete | Feb 2026 | Mar 2026
| Inventory, reports & analytics | Complete | Feb 2026 | Feb 2026
| RFID attendance tracking | Complete | Feb 2026 | Feb 2026
| Audit logs & system settings (30+ params) | Complete | Feb 2026 | Mar 2026
Phase 7: Serverless Backend (Neon PostgreSQL)
| Neon DB provisioning & Drizzle schema (16 tables) | Complete | Mar 2026 | Mar 2026
| REST API serverless function (api.mts) | Complete | Mar 2026 | Mar 2026
| Database seed function (seed.mts) | Complete | Mar 2026 | Mar 2026
| Frontend API client & hybrid store | Complete | Mar 2026 | Mar 2026
| Deploy & seed production database | In Progress | Mar 2026 | Mar 2026
Phase 8: Prototype Security & QA
| Password hashing & JWT tokens | Not Started | Mar 2026 | Apr 2026
| Server-side auth middleware & rate limiting | Not Started | Apr 2026 | Apr 2026
| Input sanitization & RBAC on API | Not Started | Apr 2026 | Apr 2026
| API testing & data integrity validation | Not Started | Apr 2026 | May 2026
| User acceptance testing (UAT) | Not Started | May 2026 | May 2026
Phase 9: Prototype Launch & Documentation
| Final prototype deploy & smoke test | Not Started | May 2026 | May 2026
| Capstone Chapter 1-5 documentation | In Progress | Mar 2026 | May 2026
| Capstone defense (Prototype) | Milestone | May 2026 | May 2026
Phase 10: Laravel Backend Setup
| Laravel project scaffolding | Not Started | Jun 2026 | Jun 2026
| Database migrations (16 tables to Eloquent) | Not Started | Jun 2026 | Jul 2026
| Eloquent models & relationships | Not Started | Jul 2026 | Jul 2026
| Auth scaffolding (Breeze/Fortify) | Not Started | Jul 2026 | Jul 2026
| Spatie permission package (7 roles, 23 perms) | Not Started | Jul 2026 | Aug 2026
| Laravel API routes & controllers | Not Started | Aug 2026 | Sep 2026
Phase 11: Vue.js + Inertia Frontend
| Vue 3 + Inertia.js setup with Laravel | Not Started | Aug 2026 | Aug 2026
| Bootstrap integration & layout components | Not Started | Aug 2026 | Sep 2026
| Port pages to Vue components (23 pages) | Not Started | Sep 2026 | Nov 2026
| Dashboard, sidebar & navigation in Vue | Not Started | Sep 2026 | Oct 2026
| Reactive forms & real-time validation | Not Started | Oct 2026 | Nov 2026
Phase 12: Full-Stack Feature Migration
| Catalog module (CRUD, LOC API, LCC, barcode) | Not Started | Sep 2026 | Oct 2026
| Circulation module (issue, return, renew) | Not Started | Oct 2026 | Nov 2026
| Reservations, fines & auto-computation | Not Started | Oct 2026 | Nov 2026
| RFID attendance & audit logs | Not Started | Nov 2026 | Nov 2026
| Reports, inventory & settings | Not Started | Nov 2026 | Dec 2026
Phase 13: Production Security & Hardening
| Bcrypt password hashing in Laravel | Not Started | Dec 2026 | Dec 2026
| Sanctum/Passport API authentication | Not Started | Dec 2026 | Dec 2026
| Laravel middleware (auth, roles, throttle) | Not Started | Dec 2026 | Jan 2027
| CSRF, XSS & SQL injection protection | Not Started | Jan 2027 | Jan 2027
| Server-side input validation (Form Requests) | Not Started | Jan 2027 | Jan 2027
Phase 14: Testing & QA (Production)
| PHPUnit & Pest feature tests | Not Started | Jan 2027 | Feb 2027
| Vue component testing (Vitest) | Not Started | Jan 2027 | Feb 2027
| Cross-browser & mobile testing | Not Started | Feb 2027 | Feb 2027
| Load testing & performance optimization | Not Started | Feb 2027 | Feb 2027
| UAT with FEATI library staff & students | Not Started | Feb 2027 | Mar 2027
Phase 15: Production Launch
| Production server deployment | Not Started | Mar 2027 | Mar 2027
| Data migration from prototype to production | Not Started | Mar 2027 | Mar 2027
| Final documentation & handover | Not Started | Mar 2027 | Mar 2027
| GO LIVE (Production) | Milestone | Mar 2027 | Mar 2027
Legend: ■ Complete ■ In Progress ■ Not Started ◆ Milestone ▌ Current Month (Mar 2026)
Phases 1-9: Prototype (Vanilla JS + Netlify + Neon PostgreSQL) ¦ Phases 10-15: Production (Vue + Inertia + Laravel + Bootstrap)
AklatBayon v2 — FEATI University — IT415 Capstone — Generated March 11, 2026